## AR
Phase | Title | Element | Subsystem | Type
Mission Ops | Battery Cell Short | Spacecraft | Power or Electrical | Flight H/W
Mission Ops | Attitude Drift During OCM-12 Tweak | Spacecraft | G&C | Flight S/W
Mission Ops | SSR Saturation (95%) During Post-Conjunction Routine Operations | Spacecraft | C&DH | Procedural
Mission Ops | Star Tracker 1 and 2 Failed Acquisition | Spacecraft | G&C | Flight H/W
Mission Ops | DSSH3 Temperature Sensor Performance | Spacecraft | Thermal | Flight H/W
Mission Ops | Routine SSR image promotion followed by rebuild PB list unexpectedly truncated | Spacecraft | C&DH | Flight S/W
Mission Ops | Magnetometer boom temperature sensor readings | Spacecraft | Thermal | Flight H/W
Mission Ops | The 13231 command load uplink was started a few minutes too soon | Spacecraft | C&DH | Procedural
Mission Ops | Latch MET Test Indicates 2ms Timing Error | Spacecraft | C&DH | Procedural
Mission Ops | G&C Reports Bad Attitude Following AST Reset | Spacecraft | G&C | Flight H/W
Mission Ops | FPP-2 Watchdog Reset | Spacecraft | Autonomy FPP | Flight H/W
Mission Ops | AST "loss-of-track" rule firings during Solar Event | Spacecraft | G&C | Procedural
Mission Ops | Tank Switch from FT1 to FT2 did not Occur during OCM-8 | Spacecraft | G&C | Flight S/W
Mission Ops | Multiple EEPROM errors when loading MP-B code application B | Spacecraft | C&DH | Flight S/W
Mission Ops | MAG powered off via FPP Rule 230 Sensor Temperature Rule | Spacecraft | Autonomy FPP | Flight S/W
Mission Ops | Commanded Momentum Dump to Wrong Target Vector | Spacecraft | G&C | Procedural
Mission Ops | FPP2 Command Execution Failure | Spacecraft | Autonomy FPP | Flight H/W
Mission Ops | Switch to AST-2 following a MASCS IPH Y-axis roll between tracks | Spacecraft | G&C | Flight H/W
Mission Ops | Leak Rate from High Pressure Helium Latch Valve Higher than Specification | Spacecraft | Propulsion | Flight H/W
Mission Ops | Unexpected Battery Discharge FPP rule 39 Fire (Heater Load Shed) | Spacecraft | Power or Electrical | Flight H/W
Mission Ops | Macro Command Execute Failure | Spacecraft | C&DH | Flight S/W
Mission Ops | Orphan file left on spacecraft after EA demotion | Spacecraft | CFDP | Flight S/W
Mission Ops | Star Trackers Loss of Attitude Knowledge for more than 4 hours | Spacecraft | G&C | Flight H/W
Mission Ops | Autonomous PDU switch (A->B) during M3 Eclipse Operations | Spacecraft | Power or Electrical | Flight S/W
Mission Ops | Pressure Based Cycling of Battery Charge Rate | Spacecraft | Power or Electrical | Flight S/W
Mission Ops | MP reset and transition to EA mode during MP-B App-B macro bin memory write | Spacecraft | C&DH | Flight S/W
Mission Ops | Stale TM_MEAS_STARS data from AST1 | Spacecraft | G&C | Flight S/W
Mission Ops | On reboot to MP 5.1, anomaly 195 was thrown indicating that either a macro and/or an autonomy rule failed to load from an EEPROM bin. | Spacecraft | C&DH | Flight S/W
Mission Ops | Incorrect s/c pointing on 5/24/09 MASCS Betelgeuse observation | Spacecraft | G&C | Procedural
Mission Ops | High Pressure Oxidizer Latch Valve Tell-tale Failure | Spacecraft | Propulsion | Flight H/W
Mission Ops | Solar Array Temperature During Vulcanoid Surveys | Spacecraft | Power or Electrical | Flight H/W
Mission Ops | AST-1 loss of lock incidents not associated with a slew or burn | Spacecraft | G&C | Flight H/W
Mission Ops | Post DSM-4 P1 Attitude Transient durring AST-1 Recovery | Spacecraft | G&C | Flight H/W
Mission Ops | AST Failure to Acquire During Pixel Dump Tests | Spacecraft | G&C | Flight H/W
Mission Ops | AST Bad Pixel Dump Process Needs FPP Autonomy Mods | Spacecraft | Autonomy FPP | Procedural
Mission Ops | Rename Anomaly Occcurs on EOF Timeouts | Spacecraft | C&DH | Flight S/W
Mission Ops | Boot MP Switched 15 V limit | Spacecraft | C&DH | Flight H/W
Mission Ops | Fuel Pressure Regulator Out of Spec during DSM-3 | Spacecraft | Propulsion | Event Report (Operational Dev)
Mission Ops | Command rejections following MP FSW 5.0 Reboot; DPU/GRS Off | Spacecraft | C&DH | Flight S/W
Mission Ops | OD116 Ephem load PAC error larger than usual (turbo unlocked) | Spacecraft | G&C | Flight S/W
Mission Ops | Pre-DSM-2 Fuel Manifold Pressure Spike | Spacecraft | Propulsion | Flight H/W
Mission Ops | AST Rule 169 Firing durring Y-axis rotations | Spacecraft | G&C | Flight H/W
Mission Ops | Autonomous switch to PSE-B | Spacecraft | Power or Electrical | Flight H/W
Mission Ops | SDST failed to lock on first try following Lunar Occulatation testing | Spacecraft | RF Comm | Flight H/W
Mission Ops | TCM-15 experienced y-axis rate oscillations resulting in magnitude under-burn | Spacecraft | G&C | Flight H/W
Mission Ops | Transient delta-V and wheel speed reactions during MASCS off-pointing activity | Spacecraft | G&C | Flight H/W
Mission Ops | G&C attitude packet has transient data point upon collection rate transitions | Spacecraft | G&C | Flight S/W
Mission Ops | IEM-B power exceeded Yellow Limit during OCXO-B warm-up period | Spacecraft | C&DH | Flight H/W
Mission Ops | Missing MASCS Command Echo Packets and High Rate Housekeeping Data | Spacecraft | C&DH | Flight S/W
Mission Ops | Unusual Behavior seen within Power System during Battery Recharge Following the SA Tilt Test | Spacecraft | Power or Electrical | Flight S/W
Mission Ops | Accelerometer B Data Anomaly at TCM-13 | Spacecraft | G&C | Flight H/W
Mission Ops | AST failed to promote after 3rd component of TCM-13 | Spacecraft | G&C | Flight H/W
Mission Ops | Extended Battery Recharge (and Transmitter On) Post Eclipse at Venus-1 | Spacecraft | Power or Electrical | Flight S/W
Mission Ops | MP-A reset on Oct 23, 2006 (DOY 296) | Spacecraft | C&DH | Flight H/W
Mission Ops | PSE VSA Control Loop Voltage Variations | Spacecraft | Power or Electrical | Flight S/W
Mission Ops | Pure Tin Use on Bus Wires | Spacecraft | RF Comm | Flight H/W
Mission Ops | Excessive pointing error when second component of TCM 11 executed on 9/12/06 | Spacecraft | G&C | Flight S/W
Mission Ops | Erroneous Readings from -Y Fanbeam & Phased Array Temperature Sensor (on TRIO A1) | Spacecraft | Thermal | Flight H/W
Mission Ops | AST-1 Reset DOY 159 00:40 | Spacecraft | G&C | Flight H/W
Mission Ops | Autonomous switch to PSE-B | Spacecraft | Power or Electrical | Flight H/W
Mission Ops | Coarse TP Ephem needs updating to match Precise Ephem and EPHCHK (Venus) | Spacecraft | G&C | Procedural
Mission Ops | TCM-10 Under-performance resulted from SA plume impingement | Spacecraft | Propulsion | Flight H/W
Mission Ops | AST1 autonomy reset after mag rolls on DOY 123 | Spacecraft | G&C | Flight H/W
Mission Ops | Commanded Momentum Dump #2 not initiated when expected on 5/11/06 DOY 131 | Spacecraft | G&C | Procedural
Mission Ops | Certain MDIS Subframing sequences can result in an MP reset | Spacecraft | C&DH | Flight S/W
Mission Ops | G&C parameter block DEMOTE contains parameter that is too small (AST data loss) | Spacecraft | G&C | Flight S/W
Mission Ops | GRS 10deg Yaw Removed due to Star Tracker Overheating | Spacecraft | Thermal | Flight H/W
Mission Ops | MAG Powered Off during MDIS Rad Cal; Sensor Temp Threshold Set Too Low | Spacecraft | Autonomy FPP | Flight H/W
Mission Ops | Feb 15 MASCS OB Scan did not detecct star; MDIS April 5 star image saw offset from expected position | Spacecraft | G&C | Procedural
Mission Ops | Auxiliary Fuel Tank Pressure Readings | Spacecraft | Propulsion | Flight H/W
Mission Ops | EA Demotion Macro has incorrect AST-1 timing | Spacecraft | Autonomy FPP | Flight S/W
Mission Ops | Post MP Reset SKI Excursions | Spacecraft | G&C | Flight S/W
Mission Ops | Poor star tracker solutions at downlink attitude on DOYs 209-213; autonomy rule 169 triggered | Spacecraft | G&C | Flight H/W
Mission Ops | Post-TCM-6 Negative Acquisition and SH Demotion | Spacecraft | G&C | Flight S/W
Mission Ops | Higher than Expected Temperatures during XRS CAS-A | Spacecraft | Thermal | Procedural
Mission Ops | Timetag Suspend Prio-3 Cmd Not Valid for Flight | Spacecraft | C&DH | Flight S/W
Mission Ops | SH Demotion Following MASCS Star Calibration | Spacecraft | G&C | Flight H/W
Mission Ops | PSE Switch to PPT Mode During MLA Power-On | Spacecraft | Power or Electrical | Flight S/W
Mission Ops | SADEA Current Exceeded YH Limits | Spacecraft | G&C | Flight H/W
Mission Ops | HSK_PM_RCS_LVA_FLANGE_TEMP_TB Violated Yellow Low Limits | Spacecraft | Propulsion | Ground C&T DB
Mission Ops | Bad data from DSS1 following flip. | Spacecraft | G&C | Flight H/W
Mission Ops | FPP1 Rule 39 (Battery Discharge & Back Ant. Heaters ON) Tripped - Back Antenna Heaters Switched Off | Spacecraft | Power or Electrical | Procedural
Mission Ops | HSK_IEM[A,B]_OXCO_TEMP_T[A,B] Yellow Low limit reached | Spacecraft | Thermal | Ground C&T DB
Mission Ops | FPP1 Rule 281 (Low Tank Temperature Part B) Tripped - TANK SEC Heater On | Spacecraft | Thermal | Flight H/W
Mission Ops | FPP AST rules 169 and 172 tripped - failover to AST2 | Spacecraft | G&C | Flight S/W
Mission Ops | HSK_DSS2_HD6_TEMP_TB Violated Low Limits Post-Flip | Spacecraft | Thermal | Ground C&T DB
Mission Ops | HSK_PM_GHE_TNK_TEMP_TB Violated Yellow Low Limits Post-Flip | Spacecraft | Thermal | Flight H/W
Mission Ops | HSK_MDS_DECK_BACK_TEMP_TB Violated Low Limits Post-Flip | Spacecraft | Thermal | Ground C&T DB
Mission Ops | AST1 Temp is above the yellow limit | Spacecraft | Thermal | Flight H/W
Mission Ops | XRS SAX box temperature is above the yellow limit. | Spacecraft | Thermal | Flight H/W
Mission Ops | GC_MODL_ERRCODE_SKI_VIOLATION anomaly count during XRS testing; | Spacecraft | G&C | Flight S/W
Mission Ops | MP TT#8 1553 Data Wrap Test Fail Tripped | Spacecraft | C&DH | Flight S/W
Mission Ops | New constraint for loading FPP macros with embedded MP/DPU commands | Spacecraft | Autonomy FPP | Procedural
Mission Ops | Target Planet Precise Ephemeris PIPO load discrepancy | Spacecraft | G&C | Ground S/W
Mission Ops | STOL Procedure CM Process | Spacecraft | C&DH | Procedural
Mission Ops | Unexpected Drop in Battery State of Charge | Spacecraft | Power or Electrical | Flight S/W
Mission Ops | FPP Autonomy Rule 169 AST1 Tripped DOY 355:16:27:01 | Spacecraft | Autonomy FPP | Flight S/W
Mission Ops | DSN requiring increase in Symbol Loop Bandwidth | Spacecraft | RF Comm | Procedural
Mission Ops | Image retrieval error flag in MDIS Cal Target Event | Spacecraft | C&DH | Flight S/W
Mission Ops | Two FPP Anomaly Counts and Three MP Counts Continuously Incrementing | Spacecraft | C&DH | Flight S/W
Mission Ops | FPP AR 169 AST1 Tripped Following STRCHK GC PB Re-load following TCM2 and after TCM3 | Spacecraft | Autonomy FPP | Procedural
Mission Ops | Safehold Demotion Did not acquire Tlm at Expected Time | Spacecraft | Autonomy FPP | Flight S/W
Mission Ops | MP Single Bit Error #1, #2, #3 & #4 | Spacecraft | C&DH | Flight H/W
Mission Ops | SH Demotion During IMU Calibration Activities | Spacecraft | Autonomy FPP | Flight S/W
Mission Ops | Buffer Pool Increasing | Spacecraft | C&DH | Flight S/W
Mission Ops | FPP2 Single Bit Error #1 #2 | Spacecraft | C&DH | Flight H/W
Mission Ops | First 'Positive Window' Transfer Layer Error Type Occurrence | Spacecraft | C&DH | Procedural
Mission Ops | Back Phased Array Antenna 8 stick pattern shifted several degrees from expected | Spacecraft | RF Comm | Flight H/W
Mission Ops | Back Phased Array Antenna Steering Opposite from Expected | Spacecraft | RF Comm | Flight S/W
Mission Ops | MP_BP1_FAILED_ALLOC alarm Red High during APID Snap | Spacecraft | C&DH | Ground S/W
Mission Ops | Burn Packet 0x418 Not Sampled at Expected Frequency for TCM-1 | Spacecraft | C&DH | Procedural
Mission Ops | OCXO Power On Voltage Trend Analysis | Spacecraft | Power or Electrical | Event Report (Operational Dev)
Mission Ops | Dump Queue Filled: MP_BP1_FAILED_ALLOC | Spacecraft | C&DH | Flight S/W
Mission Ops | Loss of telemetry during switch to OCXO | Spacecraft | RF Comm | Procedural
Mission Ops | Thruster control parameters caused additional thruster pulsing during detumble | Spacecraft | G&C | Flight S/W
Mission Ops | AST 1 Reset by FPP Autonomy Rule 169 During TCM-1 | Spacecraft | G&C | Flight H/W
Mission Ops | FPP1 Single Bit Error #2 | Spacecraft | C&DH | Flight H/W
Mission Ops | Spacecraft Rotation Rate Slowing Down during Earth Acquisition Mode | Spacecraft | G&C | Flight S/W
Mission Ops | SA Panel Current Output Different between PX and MX Panels | Spacecraft | Power or Electrical | Event Report (Operational Dev)
Mission Ops | Switched to PDU-B post launch and before First Contact | Spacecraft | Power or Electrical | Flight S/W
Mission Ops | The close all files command stopped working on Aug. 4. | Spacecraft | C&DH | Flight S/W
Mission Ops | Repeated Low Byte Count Transfer Layer Errors | Spacecraft | C&DH | Flight S/W
Mission Ops | Latch Valve Over Current Detected During the Separation Sequence Valve Flutter Activity | Spacecraft | Propulsion | Flight S/W
Mission Ops | AST 1 Failed to Promote to AAD-ATFAD Mode During Separation Sequence | Spacecraft | G&C | Flight H/W
Mission Ops | AST2 - FPP1 Rule 170 Fire | Spacecraft | G&C | Flight S/W
Mission Ops | Tank Secondary Heater Disable | Spacecraft | Propulsion | Procedural
Mission Ops | HSK_BATT_TEMP_1out of limits low | Spacecraft | Thermal | Ground C&T DB
Mission Ops | HSK_MLA_MAIN_BODY_TEMP out of low limits | Spacecraft | Thermal | Ground C&T DB

## Summary
Anomalies | End Date | Launch Date | Duration
2 | 2015-04-30 | 2004-08-03 | 3922